## Example 1
Days | Target | Done | Target Velocity | Remaining
0 | 0 | 0 | 200 | 200
1 | 10 | 3 | 190 | 197
2 | 10 | 5 | 180 | 192
3 | 10 | 8 | 170 | 184
4 | 10 | 10 | 160 | 174
5 | 10 | 8 | 150 | 166
6 | 10 | 15 | 140 | 151
7 | 10 |  | 130
8 | 10 |  | 120
9 | 10 |  | 110
10 | 10 |  | 100
11 | 10 |  | 90
12 | 10 |  | 80
13 | 10 |  | 70
14 | 10 |  | 60
15 | 10 |  | 50
16 | 10 |  | 40
17 | 10 |  | 30
18 | 10 |  | 20
19 | 10 |  | 10
20 | 10 |  | 0
200
Example Burndown Chart 1
Change Days heading to Iteration or whatever timescale is required for the bottom of the chart.
Enter the target per time period in the first cell and copy/paste to the others
Target Velocity (D2) is taken from the total (B23) and then subtracting the 'daily' target each 'day'
As each days done is entered in col C copy the last remaining in colE to the next cell down.
For more examples Google "Burndown Charts"

## Example 2
Release | Done | Remaining
350
1 | 40 | 310
2 | 50 | 260
3 | 60 | 200
4 |  | 200
5 |  | 150
6 |  | 100
7 |  | 50
Example Burndown Chart 2
Remaining column is initially set to the target total (C2) reducing in line with the target burndown
As done figure for release 1 is entered change remaining to formula (C2-B3)
As additional done figures entered copy the remaining formula down
For more examples Google "Burndown Charts"