## Cost Summary
Plymouth Life Centre Cost Report - Q3 2020/21
| Cost Heading | Budget as per Dec 2020 Approval | Spend 2013 - Date | Forecast | Total | Variance to Budget | Comments
|  | £ | £ | £ | £
Professional Fees
| Bevan Brittan | 437192 | 372149 | 65043 | 437192
| Experts | 583636 | 573636 | 10000 | 583636
| Balfour Beatty | 142554 | 142554 |  | 142554
| External Project Management Advice | 464282 | 239282 | 225000 | 464282
| Internal Legal | 74670 | 73188 | 1482 | 74670
| Internal Project Managers | 30176 | 30176 |  | 30176
| Other | 41502.84 | 41502.84 |  | 41502.84
| Condition Survey | 30000 | 0 | 30000 | 30000
|  | 1804012.84 | 1472487.84 | 331525 | 1804012.84
Enhancement Items
| Ventilation | 535805 | 0
| Extension | 350000 | 0
| LED Lighting | 510000 | 0
| Replacement Cubicles | 117232 | 0
| Upgrades to FFE | 221548 | 0
| Yoga Studio | 20000 | 0
| Other / Contingency | 175459 | 0
| Total Forecast | 1930044 | 0 | 0 | 0
Financed By:
| Initial Balfour Beatty Retention |  |  |  | -562473
| Less March 2020 Approval |  |  |  | -695521
| Less December 2020 Approval |  |  |  | -2475505
| Adverse / (Favourable) Position |  |  |  | -1929486.16

## Enhancement
PLYMOUTH LIFE CENTRE
[8 empty] | OPERATIONAL ENHANCEMENTS - DESIGN AND WORKS COST SCHEDULE | [9 empty] | Version 3.6
Ref | Cost | Prog | Decision Date | BB Design | Floor | Room No. | Location Ref. | Issue / Concern | Cost Element | Categorisation | Proposed Solution | BBCSL Comments | Instruction | Design Cost | Budget Cost | Actual Cost | Cost Variance | Decision
OE001 |  |  | Not Applicable | N | Ground & First | N/A | All Locker Areas | Plastic strip default finish constantly comes away from plinths beneath lockers | Upgrades to FFE | Operational | Plinth below lockers to be finished with a tile | Looked at on walkaround. Agreed it needs addressing. | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 0 | 11765.05 | 11765.05 | 0 | PCC009
OE002 |  |  | 15th Oct 2020 | Y | Ground & First | N/A | All toilets within changing areas, other than those classified as disabled toilets | Push button flush mechanisms difficult to use | Upgrades to FFE | COVID-19 | Replace with sensor flush mechanisms |  | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 0 | 7500 | 62087.93 | 54587.93 | PCC018
OE003 |  |  | 30th Oct 2020 | Y | Lower Ground | BL06 | Bowls Male Change | No urinal in bowls male change toilets | Upgrades to FFE | Operational | Install a urinal cubicle adjacent to existing toilet cubicles | See Quotation 33 for details | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 0 | 5000 | 2950.67 | -2049.33 | PCC029
OE004 |  |  | Not Applicable | N | All | N/A | All toilets within changing areas | Integrated soap dispensers ineffective | Upgrades to FFE | Operational | Remove and cap off | This will be done. | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 0 | 0 | 0 | 0 | PCC011
OE005 |  |  | 15th Oct 2020 | Y | First Floor | FS05 & FS09 | Male & Female Gym Change | Look and feel does not reflect the quality expected by a gym like this | Replacement Cubicles | Invest to save | Natural-looking wood and stone-effect finishes, improve ceiling and lighting. Avoid mitred corner edges. Can retain existing sinks & basins if this helps keep costs down. |  | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 2500 | 110000 | 117231.96 | 7231.96 | PCC007
OE006 |  |  | 30th Oct 2020 | Y | Ground | AQ24 | Grooming Area | Entrance doors swing both ways - also COVID-19 concerns over touch points | Upgrades to FFE | COVID-19 | Automate existing double leaf doors | Will need power and agree which way they swing | To swing into the grooming area | 0 | 10000 | 5000 | -5000 | TBC - with RK
OE008 |  |  | 20th Oct 2020 | N | Ground | AQ09 | Pool Hall | Additional manual pool hoist required | Upgrades to FFE | Operational | Provide additional manual pool hoist | PCC to procure direct |  | 0 | 7000 | 6731.99 | -268.01 | PCC to procure direct
OE009 |  |  | 20st Oct 2020 | Y | Ground | AQ09 | Pool Hall | Pool hoist sockets needed along the west side of the 50m pool | Upgrades to FFE | Operational | Install 3 additional pool hoist sockets along the west side of the 50 pool at the pool access points. (Not electrical sockets) | Note just sockets required to be on site before screed goes down | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 0 | 5000 | 5101.9 | 101.9 | PCC010
OE010 |  |  | 16th Oct 2020 (delivery of parts 30th Oct) | Y | Lower Ground | N/A | Undercroft | Lane Rope Storage system is poor and damages the ropes | Upgrades to FFE | Invest to save | Link to original specification. Consider replacing the system with one that has ramps and reels to prevent the tiles getting chipped and the ropes getting damaged | Need to ensure it doesn't breach the Mapei warranty |  | 0 | 10000 | 11310 | 1310 | PCC to procure direct
OE011 |  |  | 30th Oct 2020 | Y | Ground | AQ09 | Pool Hall | Less-energy efficient lighting | LED Lighting | Invest to save | Upgrade lighting to LEDs |  | Please provide a fully costed design for this piece of work | 6840 | 500000 | 354040.38 | -145959.62 | PCC028
OE012 |  |  | 30th Oct 2020 | Y | Ground |  | Wet & Dry side Changing Areas | Less-energy efficient lighting | LED Lighting | Invest to save | Upgrade lighting to LEDs |  | Please provide a fully costed design for this piece of work |  | 60000 | 148552.11 | 88552.11 | PCC034
OE013 |  |  | 30th Oct 2020 | Y | First | FS05 & FS09 | Male & Female Gym Change | Less-energy efficient lighting | LED Lighting | Invest to save | Upgrade lighting to LEDs |  | Please provide a fully costed design for this piece of work | 1920 | 60000 | 40000 | -20000 | TBC - with RK
OE014 |  |  | 1st Oct 2020 | Y | Ground | AQ09 | Pool Hall | Timing Cable seems to be intermitent and causing timing issues. Potentially due to water ingress | Upgrades to FFE | Operational | Replace / repair the timing cable within the works in the pool hall | Cables are currently being tested and are fine | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 0 | 30000 | 0 | -30000 | PCC to procure direct
OE015 |  |  | Not Applicable | Y | Ground | AQ09 | Pool Hall | Outside lane sees water splash from swimmer to wash back and create unfair resistance to swimmer | Upgrades to FFE | Operational | 25m and 50m competition pools require additional lane rope hooks on the outside of both of the outside lanes. | BBCSL would prefer SLM / Variopool to undertake this work outside of BB's work | Please provide a design cost if appropriate and a full cost (where available at this time) for the delivery / installation of this piece of work. | 0 | 10000 | 10000 | 0 | PCC to procure direct
OE016 |  |  | Not Applicable | N | Ground | AQ09 | Pool Hall | Outside lane sees water splash from swimmer to wash back and create unfair resistance to swimmer | Upgrades to FFE | Operational | 25m and 50m competition pools require additional lane ropes on the outside of both of the outside lanes. | PCC to procure direct |  | 0 | 10000 | 0 | -10000 | PCC to procure direct
OE017 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU01A - Pool Hall | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 1000 | 78800 | 68086.62 | -10713.38 | PCC013
OE018 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU01B - Pool Hall | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 1000 | 78800 | 68086.62 | -10713.38 | PCC013
OE019 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU01C - Pool Hall | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 1000 | 78800 | 68086.62 | -10713.38 | PCC013
OE020 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU02 - Sports Hall | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 39529.4 | 39529.4 | 0 | PCC013
OE021 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU03 - Multipurpose | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 25408.84 | 25408.84 | 0 | PCC013
OE022 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU04 - Gym | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 19844.8 | 19844.8 | 0 | PCC013
OE023 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU05 - Dry Dive | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 14723.19 | 14723.19 | 0 | PCC013
OE024 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU06 - Dry Change / General | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 24963.42 | 24963.42 | 0 | PCC013
OE025 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU07 - Wet Change | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 26981.23 | 26981.23 | 0 | PCC013
OE026 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU08 - Climbing | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 16866.68 | 16866.68 | 0 | PCC013
OE027 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU09 - Bowls Hall | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 80000 | 18943.7 | -61056.3 | PCC013
OE028 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU10 - Squash | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 16709.46 | 16709.46 | 0 | PCC013
OE029 |  |  | 21st Oct 2020 | Y | Roof | N/A | AHU11 - Kitchen Supply | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | BBCSL looking into | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 10332.69 | 10332.69 | 0 | PCC013
OE029a |  |  | 21st Oct 2020 | N | Roof | N/A | N/A | Improved HVAC in line with COVID-19 guidance. | Ventilation | COVID-19 | Requires a design review | Associated costs for AHU work - craneage, flushing etc | Please provide a design & cost to upgrade system in line with COVID-19 guidelines. | 0 | 317241.55 | 317241.55 | 0 | PCC013
OE030 |  |  | 2nd Nov 2020 | N | Ground | AQ09 | Pool Hall | Existing PA system is poor | Other / Contingency | Capital | Upgrade PA system - specification to be agreed | PA system serves the whole building. Poor acoustics in the Pool Hall are the main hurdle | Please provide a cost for this piece of work utilising existing infratructure if possible | 0 | 10000 | 0 | -10000 | Descoped - to be picked up at a later stage
OE031 |  |  |  | Y | Ground | AR01 AR02 | Entrance Foyer and Lobby | Poor entrance way | Extension | Capital | Build new extended lobby and entrance way out in to the curteledge of the building inside the Glulam beams | BBCSL looking into | Please provide a cost for this piece of work utilising existing structures where possible | 37591.69 | 0 | 0 | 0 | PCC032 (Design cost only)
OE032 |  |  |  | Y | First Floor |  | Steam Room & Sauna | Could be opened up to use as a yoga space | Yoga Studio | Capital | Remove these rooms (plus treatment rooms?) and open up the space | BBCSL looking into |  | 0 | 20000 | 30000 | 10000 | TBC - with RK
OE042 |  |  |  | Y | Ground | AN57 | Corridor | A larger pram / buggy storage area is needed outside the changing village | Other / Contingency | Capital | Remove some banks of lockers along the corriror and create a recessed pram / buggy storage area |  |  | 0 | 5000 | 1000 | -4000 | TBC - with RK
OE043 | [7 empty] | Wi-Fi in PLC is poor | Other / Contingency | Capital | Upgrade Wi-Fi to improve signal | Not BBCSL work |  | 2500 | 25000 | 25000 | 0 | PCC to procure direct
OE044 |  |  |  | Y | Ground & First Floor |  | All changing areas | Mitred skirting corners and edges have provided Operational and H&S issues | Upgrades to FFE | Operational | Avoid mitred skirting corners and edges when new floors are laid | Can be done. There may be a minimal cost at most |  | 0 | 0 | 0 | 0 | PCC003
OE045 |  |  |  | Y | Ground | AQ09 | Pool Hall | Need for an additional diving harness installed on to 1 metre board | Upgrades to FFE | Capital | Install an additional harness |  |  | 0 | 30000 | 30354.3 | 354.3 | PCC to procure direct
OE045a |  |  |  | Y | Ground | AQ10 | Pool Hall | Need for an additional diving harness installed on to 1 metre board | Upgrades to FFE | Capital | Install an additional harness | Will require a design feasibility | Proceed with feasibility to assess if a harness can be installed | 5750.17 | 0 | 0 | 0 | PCC031
OE045b |  |  |  | Y | Ground | AQ09 | Pool Hall | Need for an additional diving harness installed on to 1 metre board | Upgrades to FFE | Capital | Install an additional harness | Scaffold to allow for installation |  | 0 | 0 | 23235.85 | 23235.85 | PCC040
OE046 |  |  |  | Y | First Floor | FS01 | First Floor Gym | Less-energy efficient lighting | LED Lighting | Invest to save | Upgrade lighting to LEDs |  | Please provide a fully costed design for this piece of work | 0 | 30852.88 | 30852.88 | 0 | PCC026
OE047 |  |  |  | Y | First Floor | DS19 | Dry Dive | Less-energy efficient lighting | LED Lighting | Invest to save | Upgrade lighting to LEDs |  |  | 960 | 30000 | 9667.24 | -20332.76 | PCC037
OE048 |  |  |  | N/A | N/A | N/A | N/A |  | Other / Contingency | Capital |  | Enhancement works require a Finishes Manager to ensure they are delivered correctly | Please provide a cost for this additional resource | 0 | 0 | 30178.61 | 30178.61 | PCC035
OE049 |  |  |  | N/A | N/A | N/A | N/A |  | Other / Contingency | Capital |  | Combined design costs for the Yoga Suite, Changing Village and Gym Change |  | 14893.34 | 0 | 0 | 0 | PCC033
OE050 |  |  |  | N/A | Ground | AQ09 | Pool Hall | Dive tower lighting is poor | Other / Contingency | Operational | Replace the trespa panels and upgrade the dive tower lighting. See Quotation 49 for details | See Quotation 49 for details |  | 0 | 40882.78 | 40882.78 | 0 | PCC043
OE051 |  |  |  | To match existing | Ground | AQ09 | Pool Hall | There needs to be a (removable) barrier to prevent people running through the new opening straight on to poolside | Other / Contingency | COVID-19 | Install relevantly sized poolside barrier (to match the existing) | See Quotation 50 for details |  | 0 | 22615.48 | 22615.48 | 0 | PCC044
OE052 |  |  |  |  | Ground | AQ16 | Changing Village | There needs to be a metal shutter at the new poolside entrance which can be locked shut to restict access when operationally required | Other / Contingency | COVID-19 | Install shutter, similar to others already in situ |  |  | 0 | 20000 | 10000 | -10000 | TBC - with RK
OE053 |  |  |  |  | Ground | AR02 | Reception | Reception Desk and Café Servery are looking worn | Upgrades to FFE | Operational | Re-clad existing to extend operational lifespan |  |  | 0 | 50000 |  | -50000 | PCC to procure direct
OE054 |  |  |  |  | Ground | AR02 | Reception | Café furniture loooking tired and worn | Upgrades to FFE | Operational | Replace, potentially in line with what is in The Box |  |  | 0 | 50000 |  | -50000 | PCC to procure direct
OE055 |  |  |  | N/A | All | Various | All of Site | Update / Renew wayfinding signage | Other / Contingency | Operational | Replace damaged like for like. Update existing where possible |  |  | 0 | 7743.9 | 8117.4 | 373.5 | PCC to procure direct
OE056 |  |  |  | N/A | Ground | CL01 | Climbing Area | Look into feasibility for creating a mezzanine floor within the climbing area | Other / Contingency | Invest to save |  | Atkins to undertake an initial feasibility study |  | 0 | 2500 | 2500 | 0 | PCC048
[13 empty] | Totals | 75955.2 | 2009861.35 | 1850936.55 | -234880
[7 empty] | Ventilation | 735804.82
[7 empty] | Extension | 0
[7 empty] | LED Lighting | 583112.61
[7 empty] | Replacement Cubicles | 117231.96
[7 empty] | Upgrades to FFE | 94684.71
[7 empty] | Yoga Studio | 30000
[7 empty] | Other / Contingency | 140294.27
1701128.37
-469760

## Design and Work Cost Schedule
{Organisation Name} {Project Name} – Design and Work Cost Schedule Plan
Reference | Floor | Room | Location reference | Customer concern | Proposed solution | Contractor comment | Contractor instruction | Quote | Budget cost | Actual Cost | Cost variance | Payment | Priority | Complete | Responsible | Notes
Theme
ABC123 | Ground floor | 123 | XXX | XXX | XXX | XXX | XXX | 0 | 0 | 0 | 0 | Customer | High | No | Name | XXX
ABC123 | First floor | 456 | XXX | XXX | XXX | XXX | XXX | 0 | 0 | 0 | 0 | Contractor | Medium | Yes | Name | XXX
Theme
ABC123 | Ground floor | 123 | XXX | XXX | XXX | XXX | XXX | 0 | 0 | 0 | 0 | Customer | Low | No | Name | XXX
ABC123 | First floor | 456 | XXX | XXX | XXX | XXX | XXX | 0 | 0 | 0 | 0 | Contractor | High | Yes | Name | XXX
Theme
ABC123 | Ground floor | 123 | XXX | XXX | XXX | XXX | XXX | 0 | 0 | 0 | 0 | Customer | Medium | No | Name | XXX
ABC123 | First floor | 456 | XXX | XXX | XXX | XXX | XXX | 0 | 0 | 0 | 0 | Contractor | Low | Yes | Name | XXX